## 4R
2020 New Model Schedule | [29 empty] | PREPARE BY. | S.Saisunee
MODEL | CUSTOMER |  | JAN |  |  | FEB |  |  | MAR |  |  | APR |  |  | MAY |  |  | JUN |  |  | JUL |  |  | AUG |  | SEP | OCT | NOV |  | DEC |  | Remark
TLAX(CBU) | HATC |  |  | RYOKAKU Mid Jan'20 | [5 empty] | MP Begin Mar'20 | [21 empty] | BASE
|  | Pan | [29 empty] | TLAY
Actual
[5 empty] | 2020-01-17 | [8 empty] | 2020-04-29
T00A ( AP2) | HATC |  |  | HIN Begin Jan'20 |  |  | RC EVENT Mid May'20 | [5 empty] | MP END APR'20 | [18 empty] | NEW FULL
| for | Pan
HMSB
Actual
[5 empty] | 2020-01-08 | [5 empty] | 2020-03-06 |  |  | 2020-04-07
T00A ( AP2) | HATC |  |  | DAN Begin Jan'20 | [27 empty] | NEW FULL
Pan
Actual
2020-01-09
4L45W 20MY | MMTH |  |  | PT2 Begin Jan'20 | [14 empty] | MP Mid Jun'20 | [12 empty] | BASE
Groub 2 for GCC |  | Pan | [29 empty] | 4P45
Actual
[8 empty] | 2020-02-25 | [11 empty] | 2020-06-29
T00A 5D | HATC |  |  | SHOKEN |  |  | SHOKEN | [5 empty] | DAN Begin Apr'20 | [8 empty] | HIN Mid Jul'20 | [8 empty] | MP Mid Dec'20 | BASE
|  | Pan | [29 empty] | T00A AP7
Actual
[5 empty] | 2020-01-22 | [11 empty] | 2020-05-26
TLAX | HATC | [11 empty] | MP Mid Apr'20 | [18 empty] | BASE
for HPM Desitination |  | Pan | [29 empty] | TLAY
78100TMM N430M1
| 78100TMM N310M1 | Actual
| 78100TMM N530M1 |  |  |  | 2020-01-27 | [8 empty] | 2020-04-10
TLAX | HATC | [5 empty] | HIN End Feb'20 | [5 empty] | RC Begin Apr'20 |  |  | MP End May'20 | [15 empty] | BASE
for HTW Desitination |  | Pan | [29 empty] | TLAY
78100TMM F030M1
| 78100TMM F230M1 | Actual
| 78100TMM F330M1 |  |  |  | 2020-01-17 | [5 empty] | 2020-03-17 | [8 empty] | 2020-06-30
TLAX | HATC | [6 empty] | RYO Begin Feb'20 | [23 empty] | BASE
for HCIL Desitination |  | Pan | [29 empty] | TLAY
78100TMVXB910M1
| 78100TMTXB810M1 | Actual
| 78100TMSXB010M1 | [12 empty] | 2020-04-16
TLAX | HATC | [5 empty] | HIN End Feb'19 | [5 empty] | RYO Begin Apr'20 |  |  | MP End May'20 | [15 empty] | BASE
for HVN Desitination |  | Pan | [29 empty] | TLAY
78100TMD V030M1
| 78100TMD V130M1 | Actual
| 78100TMD V230M1 | [6 empty] | 2020-02-21 | [5 empty] | 2020-04-08 | 2020-04-28
TLAX | HR0480-4XX |  |  | HIN Begin Jan'20 | [8 empty] | MP All Variation start delivery from 20 Apr'20 | [18 empty] | BASE
for HM | HR0477-3XX | Pan | [29 empty] | TLAY
Actual
[5 empty] | 2020-01-23 | [8 empty] | 2020-04-10
T20A CBU | HATC | [14 empty] | DAN0 Begin May'20 | [8 empty] | DAN Mid Aug'20 |  |  |  | HIN Mid Nov'20 |  |  | NEW FULL | RYO Mid Feb'21
RH |  | Pan | [30 empty] | MP Begin Apr'21
Actual
T00A ( AP2) | HATC | [5 empty] | DAN Begin Feb '20 | [5 empty] | HIN Begin Apr'20 |  |  | RC End May'20 | [5 empty] | MP Mid Jul'20 | [9 empty] | NEW FULL
HVN |  | Pan
78100T00AZZ13M1
Actual
[14 empty] | DAN 6/4/20 |  |  | HVN FOR TEST 7/5/20
T20A | HATC | [11 empty] | DAN0 Begin Apr'20 | [11 empty] | DAN Begin Aug'20 | [5 empty] | HIN Begin Dec'20 | NEW FULL | RYO Mid Feb'21
HASB |  | Pan | [30 empty] | MP Begin Mar'21
Actual
T20A | HATC | [11 empty] | DAN0 Begin Apr'20 | [11 empty] | DAN Begin Aug'20 | [5 empty] | HIN Begin Dec'20 | NEW FULL | RYO Mid Feb'21
HACPL |  | Pan | [30 empty] | MP Begin Mar'21
Actual
T20A | HATC | [29 empty] | DAN0 Begin Dec'20 | NEW FULL | DAN Begin Apr'21
HCIL |  | Pan | [30 empty] | HIN Begin Aug'21
RYO End Oct'21
|  | Actual | [30 empty] | MP Mid Nov'21
T20A | HATC | [20 empty] | DAN0 13 Jul'20 | [6 empty] | DAN Mid Nov'20 |  |  | NEW FULL | HIN Begin Feb'21
LH for HATC |  | Pan | [30 empty] | RYO Begin Jun'21
MP Mid Jul'21
Actual
DAN0 9/7/20
4B45V20MY | MMTH | [11 empty] | PJL 10 Apr'20 | [8 empty] | PT Begin Aug'20 | [8 empty] | PP Begin Dec'20 | BASE
| 8100C933 | Pan | [29 empty] | 4P45
Actual
PJL 27/5/2020
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Pan
Actual
Note on E5: HR0480511KRCO01TH 2 Pcs HR0480510KRCO01TH 1 Pcs. HR0480513KRCO01TH 1 Pcs. HR0480512KRCO01TH 1 Pcs. HR0480540KRCO01TH 1 Pcs. HR0480520KRCO01TH 1 Pcs. HR0480519KRCO01TH 1 Pcs. HR0480502KRCO01TH 1 Pcs.
Note on M5: HR0480520CRCO01TH 10 PCs.
Note on Q10: HR0490010KRCO07Th 30 PCs.
Note on E15: HR0490019KRCO04TH 2 Pcs. HR0490036KRCO04TH 1Pcs HR0490043KRCO04TH 1 Pcs HR0490028KRCO04TH 1Pcs HR0490031KRCO04TH 1Pcs HR0490034KRCO04TH 2Pcs HR0490042KRCO04TH 1Pcs HR0490026KRCO04TH 2Pcs HR0490046KRCO04TH 1Pcs HR0490048KRCO04TH 4Pcs HR0490045KRCO04TH 5Pcs HR0490039KRCO04TH 2Pcs HR0490024KRCO04TH 6Pcs HR0490053KRCO00TH 2Pcs
Note on AC24: METER 6 AUG'20
Note on E25: HR0490003KRCO04TH 3 Pcs.
Note on I30: 78100TMM N530M1 1 Pcs.
Note on I35: HR0480531KRCO01TH HR0480535KRCO01TH HR0480532KRCO01TH
Note on Q40: HR0480541KRCO02TH = 5 PCs.
Note on I45: HR0480530KRCO01TH 1 Pcs. HR0480534KRCO01TH 1Pcs.
Note on Q45: HR0480534KRCOTH 1 Pc. HR0480534KRCOTH 1Pcs.
Note on E50: HR0480404KRCO01TH 2 Pcs. HR0480406KRCO01TH 2 Pcs. HR0477315KRCO01TH 2 Pcs. HR0477301KRCO01TH 2 Pcs.
Note on U55: HR0492209KRCO01TH 1 Pcs. HR0492224KRCO01TH 1 Pcs HR0491207KRCO01TH 2 Pcs.
Note on AG55: HR0492206KRCO _ _TH 1 Pcs. HR0492209KRCO _ _TH 6 Pcs. HR0492215KRCO _ _TH 2 Pcs HR0492224KRCO _ _TH 3 Pcs. HR0491204KRCO02TH 1 Pcs. HR0491203KRCO02TH 3 Pcs. HR0491207KRCO02TH 11 cs.
Note on I60: HR0490037KRCO07TH 1 Pcs. HR0490029KRCO07TH 1 Pcs. HR0490032KRCO07TH 1 Pcs. HR0490035KRCO07TH 1 Pcs.
Note on AC80: 78100T21 T010M1 1 Pcs. 78100T20 T010M1 1 Pcs.

## 2R
2020 New Model Schedule | [40 empty] | PREPARE BY. | S.Saisunee
MODEL | CUSTOMER |  | JAN |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  | AUG |  |  | SEP |  |  |  | OCT |  |  | NOV |  |  | DEC |  |  | Remark
MKPF | THM | [20 empty] | PP-3 = Jul (ETD TNS around End of 25 Jun) |  | MP = Jul (ETD TNS 29 Jun) | [19 empty] | Base
METER ASSY COMB | HP1186021N0CE03 | Pan | [41 empty] | MKPA
TNS => THM | HP1186022N0CE03
35,119 pcs/2Y |  | Actual
[23 empty] | PP3 17 JUN'20 | 1ST MP 23 JUN'20
K2EA | THM |  |  | THM PP-2 = 13/Feb (ETD TNS 30/Jan) | [6 empty] | THM PP-3 = 12/Mar (ETD TNS 10/Mar) | [32 empty] | New Full
METER ASSY COMB |  | Pan
TNS => THM
20,275 pcs/2Y |  | Actual
[8 empty] | PP3 24 FEB'20 |  |  | 1ST 10 MAR'20
C69(KPTT) | KUBOTA | [5 empty] | 'MP KMA(US) Apr'20 (ETD TNS Early of Feb'20 by sea) | [36 empty] | Base
TNS =>KPTT => | KU0200007NRCO | Pan | [41 empty] | C53 EU
KMA(US) =>EU | KU0200006NRCO | [42 empty] | (KU0200004NRCO)
1,800 pcs/Y |  | Actual
1ST MP 20 JAN'20
3905 21MY | KMT | [16 empty] | KMT Pilot (1-Jun-20) = ETD TNS 1-May-20 | [10 empty] | KMT Pre-MP (1-Sep-20) = ETD TNS 1-Aug-20 | KMT MP (15-Sep-20) = ETD TNS 15-Aug-20 | [13 empty] | Base
TNS -> KMT | KA0512003K0CX00 | Pan | [41 empty] | 3905
[16 empty] | INT PILOT 23 APR'20 | [27 empty] | (25031-0705 ,
13,000 pcs/2Y |  | Actual | [41 empty] | KA0512002K0CX)
2504 | KMT | [5 empty] | KMI Pre-MP(Mid of Mar'20) = ETD TNS Early of Feb'20 (by SEA) |  | KMI 1st MP(1-Apr'20) = ETD TNS Mid of Feb'20 (by SEA) | [8 empty] | KMT Pre-MP(Early of Jun'20) = ETD TNS early of May'20 |  | KMT 1st MP(Mid of Jun'20) = ETD TNS Mid of May'20 | [23 empty] | Base
TNS -> KMT | KA0525001K0CX | Pan | [41 empty] | 8896
TNS -> KMT -> KMI | KA0525003K0CX | [6 empty] | KMI PRE-MP & 1ST MP 6 FEB'20 |  |  |  |  | KMT 1ST MP 31 MAR'20 | [30 empty] | (25031-0787 ,KA0520004K0CX)
18,555/2Y | KA0525002K0CX | Actual
[8 empty] | PRE-MP & 1ST MP 6 FEB'20 | [5 empty] | KMT 1ST MP 01 APR'20
4810 21MY | KMT | [20 empty] | KMT Pilot (1-July-20) = ETD TNS 1-Jun-20 | [8 empty] | KMT Pre-MP (1-Oct-20) = ETD TNS 1-Sep-20 |  |  | KMT MP (16-Oct-20) = ETD TNS 16-Sep-20 | [9 empty] | Base
TNS -> KMT | KA0511003K0CX00 | Pan | [41 empty] | 4810 current
INT PILOT 21 MAY'20
21,600/2Y |  | Actual
PILOT 5 JUN'20
B2J |  |  |  | STEP3 (apply antifog on upper case) |  |  |  | Add TEMISH on lower case '7-Feb-20 | [35 empty] | New Full | STEP3 (apply antifog on upper case)
| YA1238001 | Pan | [43 empty] | YA1238101K0CE02 : 23-Dec-19
| YA1238002 |  |  |  | ACRY SHUT 14 JAN'20 (YA1238111) |  |  | Add TEMISH 11 JAN'20 | [37 empty] | YA1238102K0CE02 : 7-Feb-20
15,000/Y | YA1238003 | Actual | [43 empty] | YA1238111K0CE02 : 7-Feb-20
[5 empty] | ACRY SHUT 18 JAN'20 (YA1238111) |  |  | Add TEMISH 24 JAN'20 | [36 empty] | Add TEMISH on lower case '7-Feb-20
SCM7T4 | NSSD | [24 empty] | 'Pilot1 KCW(china) Sep'20 (ETD TNS 31-July-2020) | [9 empty] | MP KCW(china) Dec'20(ETD TNS Mid of Oct'2020) | [7 empty] | Base
TNS =>NSSD => KCW | RF716-5311-1 | Pan | [41 empty] | MB43
(Wuxi, China) | KU0196003NRCOCN | [42 empty] | (KU0196002NRCO)
1,000/Y |  | Actual
8121 / 8122 | KMT | [16 empty] | KMT Pilot : Early of Jun'20 = ETD TNS Early of May'20 | [10 empty] | KMT Pre-MP End of Sep'20 = ETD TNS Mid of Aug'20 |  |  | KMT MP : Early of Oct'20 = ETD TNS Early of Sep'20 | [11 empty] | Base
METER ASSY | KA0528001N0CE00 | Pan | [41 empty] | 8020/8022
TNS -> KMT | KA0528002N0CE00 | [20 empty] | INT PILOT 5 JUN'20 | [21 empty] | KA0447001N0CE
9,615/2Y |  | Actual | [41 empty] | KA0447003N0CE
PILOT 09 JUL'20
MB23SI | KBM |  |  | 'KBM Pilot1 = Mar'20 (ETD TNS Mid of Jan'20) | [6 empty] | 'KBM Pilot2 = May'20 (ETD TNS Mid of Mar'20) | [27 empty] | 'KBM MP = Jan'21 (ETD TNS Mid of Nov'20) |  |  |  |  | Base
TNS -> KBM | KU0196006NRCO01DE | Pan | [41 empty] | MB43
[8 empty] | INT PILOT1 18 FEB'20 | [35 empty] | (KU0185002NRCO01DE)
50 pcs/Y |  | Actual
INT PILOT1 18 FEB'20
K1TA | THM | [13 empty] | THM PP-1 = 23/Apr (ETD TNS 6/Apr) | [13 empty] | THM PP-2 = 4/Sep (ETD TNS 19/Aug) | [6 empty] | THM PP-3 = 27/Oct (ETD TNS 22/Oct) | THM 1st MP = 3/Nov (ETD TNS 30/Oct) | [6 empty] | Base
METER ASSY COMB | HP-1229-XXX | [20 empty] | Add - THM PP-1 lot 2 = 15/May (ETD TNS 30/Apr 9 Jun'20) | [21 empty] | KZZJ
TNS => THM | [15 empty] | INT 20 APR'20 | INT 27 APR'20
32,700 pcs/2Y |  | Actual
(All part number) | [15 empty] | PP1 24 APR'20 | [6 empty] | PP1 LOT2 4 JUN'20
K1BA (STD TYPE) | THM |  |  | THM PP-1 = 4/Feb (ETD TNS 24/Jan) | [10 empty] | THM PP-2 = 12/May (ETD TNS 20/Apr) | [6 empty] | THM PP-3 = 25 JUN (ETD TNS 23/Jun) |  | THM MP = 2 JUL (ETD TNS 30/Jun) | [19 empty] | Base
METER ASSY COMB | 37100-K1B-T020-M1 | Pan | [41 empty] | K0BA
TNS => THM | 37100-K1BA-F011-M1 |  |  |  | M3 INTERNAL 29 JAN'20 | [10 empty] | M3 INTERNAL 15 APR'20
32,400 pcs/2Y | 37100-K1BA-H012-M1 | Actual
[5 empty] | PP1 29 JAN'20 | [10 empty] | PP2 23 APR'20 | [6 empty] | PP3 & 1ST MP 16 JUN'20
K1BA (SEB TYPE) | THM | [20 empty] | THM PP-2 = 16/Jun (ETD TNS around 9/Jun) | [6 empty] | THM PP-3 = 21 Aug (ETD TNS 19/Aug) | THM MP = 28 Aug (ETD TNS 26/Aug) | [13 empty] | Base
METER ASSY COMB | 37100-K1BA-K120-M1 | Pan | [41 empty] | K0BA
TNS => THM | 37100-K1BA-T120-M1
8,820 pcs/2Y | 37100-K1BA-U120-M1 | Actual
PP2 26 MAY'20
E67 | KUBOTA | [20 empty] | KPTT Pilot = 1-Jun 8-Jul-20 | [9 empty] | '1st Lot = 1-Sep'20 | [11 empty] | Base
METER COMB | KU0188015 NRCO00 | Pan | [41 empty] | E62
[20 empty] | INT PILOT 21 MAY'20 | [23 empty] | (KU0188001NRCO)
840/Y |  | Actual
PILOT 30 JUN'20
C53 FULL MODEL CHANGE (C87) | KTPP | [30 empty] | Pilot = Sep'20 (KPTT) | [6 empty] | 'MP=Nov'20 (KPTT) |  |  |  |  | Base
METER COMB | KU0200011XXXXXX | Pan | [41 empty] | C53
TNS -> KPTT | KU0200012XXXXXX
24,000/Y | KU0200013XXXXXX | Actual
K40H | NSEU | [9 empty] | 'PP1 =HII : 9-Apr'20 , NSEU 19-Mar (ETD TNS 16-Mar'20 (Latest) by AIR) | [10 empty] | PP2 =HII :6July'20, NSEU 15-Jun (ETD.TNS 1 Jun'20 by AIR) HII 15-Sep'20 (ETD.TNS 17-Aug'20 by AIR) | [8 empty] | 'PP3 =HII : 26-Oct'20 , NSEU 5-Oct'20 (ETD.TNS 14Sep'20 by AIR) HII 1-Dec'20 (ETD.TNS End of Oct'20 by AIR) | [12 empty] | Base
(NSEU) | 37100-K40H-A000 EU Mile | Pan | [30 empty] | 'MP =HII : 17-Nov'20 , NSEU 3-Nov'20 (ETD.TNS 14Sep'20 by SEA) HII 14-Dec'20 (ETD.TNS Mid-End of Oct'20 by AIR) | [10 empty] | K40G
TNS--> NSEU-->HII | 37100-K40H-B000 UK Mile | [10 empty] | INT PP1 13 MAR'20 | [6 empty] | INT PP2 26 MAY'20
22,000/2Y |  | Actual
INT PP1 13 MAR'20
K1BF | NSEU | [9 empty] | 'PP1 =HII : 9-Apr'20 , NSEU 19-Mar (ETD TNS 16-Mar'20 (Latest) by AIR) | [11 empty] | 'PP2 =HII :6July'20, NSEU 15-Jun (ETD.TNS 1 Jun'20 by AIR) HII 15-Sep'20 (ETD.TNS 17-Aug'20 by AIR) | [8 empty] | 'PP3 =HII : 26-Oct'20 , NSEU 5-Oct'20 (ETD.TNS 14Sep'20 by AIR) HII 1-Dec'20 (ETD.TNS End of Oct'20 by AIR) |  |  |  | 'MP =HII : 17-Nov'20 , NSEU 3-Nov'20 (ETD.TNS 14Sep'20 by SEA) HII 14-Dec'20 (ETD.TNS Mid-End of Oct'20 by AIR) | [7 empty] | Base
(NSEU) | 37100-K1BF-D000 EU Km/L | Pan | [41 empty] | K0BF
TNS--> NSEU-->HII | 37100-K1BF-E000 UK Mile | [10 empty] | INT PP1 17 MAR'20 | [5 empty] | INT PP2 19 MAY'20
22,000/2Y |  | Actual
PP1 17 MAR'20
K1BF(SAB) | NSEU | [42 empty] | Base
(NSEU) | 37100-K1BF-D210 | Pan | [41 empty] | K1BF
TNS--> NSEU-->HII | 37100-K1BF-E210
3,600/Y |  | Actual
K98G | THM | [24 empty] | THM PP-1 = Aug (ETD TNS around Mid of Jul) | [9 empty] | THM PP-3 = Nov'20 (ETD TNS around End Oct) |  |  | THM MP = Nov'20 (ETD TNS around Early Nov) |  |  |  |  | Base
METER ASSY COMB |  | Pan | [41 empty] | K98A
TNS => THM
15,420 pcs/2Y |  | Actual
K0AJ | THM | [42 empty] | Base | THM PP-1 Aug'21
METER ASSY COMB | HP1150009 N0CE | Pan | [41 empty] | K0AH | THM PP-2 Dec'21
TNS => THM | [44 empty] | THM PP-3 Jan'22
18,967 pcs/2Y |  | Actual | [42 empty] | THM MP Jan'22
K26P | THM | [13 empty] | THM PP-1 = 11/May (ETD TNS 27/Apr) | [10 empty] | THM PP-2 = 10/Aug (ETD TNS 18/Jul) | [5 empty] | THM PP-3 = 10/Sep (ETD TNS 8/Sep) |  | THM 1st MP = 24/Sep (ETD TNS 22/Sep) | [9 empty] | Base
METER ASSY COMB | HP-1250-XXX | Pan | [41 empty] | K26J
TNS => THM | [15 empty] | INT 23 APR'20
89,080 pcs/2Y |  | Actual
PP1 27 APR'20
MKYA | THM | [5 empty] | THM PP-1 = 19/MAR (ETD TNS 26/Feb) | [14 empty] | THM PP-2 = 7/JUL (ETD TNS 22 24/Jun) | [6 empty] | THM PP-3 = 24/AUG (ETD TNS 20/Aug) | THM MP =28/ AUG (ETD TNS 26/Aug) | [13 empty] | Base
METER ASSY COMB | HP1182021,022,025,026,029,030N0CE01 | Pan | [41 empty] | MKNA
TNS => THM | [7 empty] | INT 20 FEB'20
43,100 pcs/2Y |  | Actual | [5 empty] | PP1 21 FEB'20 | [14 empty] | PP2 17 JUN'20
K1MA-T | THM | [9 empty] | THM PP-1 = 26/Mar (ETD TNS 6/Mar) | [10 empty] | THM PP-2 = 25/Jun (ETD TNS around 6/Jun 8/Jun) |  |  |  | THM PP-3 = 13/Aug (ETD TNS 29/Jul) |  |  | THM MP = 27/Aug (ETD TNS 13/Aug) | [14 empty] | Base
METER ASSY COMB | HP1238001K0SX02 | Pan | [15 empty] | THM PP-1 Korea Type = 20/May (ETD TNS 11/May) | [25 empty] | K76L
TNS => THM | [11 empty] | INT 9 MAR'20 | [6 empty] | 7 MAY'20
137,400/2Y |  | Actual
[12 empty] | PP1 11 MAR'20 | [6 empty] | PP1(Korea) 12 MAY'20 |  |  |  | PP2 2 JUN'20
K1MA-W000 => K2JA | THM | [24 empty] | THM PP-1 = 24/Jul (ETD TNS 9/Jul 8/Jul) | [9 empty] | THM PP-2 = 27/Oct (ETD TNS 5/Oct) | [5 empty] | THM PP-3 = 16/Dec (ETD TNS 14/Dec) | THM MP = 24/Dec (ETD TNS 22/Dec) | Base
METER ASSY COMB | HP1252001K0CX01 | Pan | [41 empty] | K58M
TNS => THM | [23 empty] | INT 22 JUN'20
1,213,300/2Y |  | Actual
PP1 29 JUN'20
K2AA | THM | [13 empty] | THM PP-1 12/May (ETD TNS 24/Apr) | [23 empty] | THM PP-3 18/Nov (ETD TNS 16/Nov) | THM 1st MP 25/Nov (ETD TNS 23/Nov) |  |  |  | Base
METER ASSY COMB | HP1152101 K0CX01 | Pan | [41 empty] | K1BA
TNS => THM | [15 empty] | INT 13 APR'20
5,000/2Y |  | Actual
PP1 17 APR'20
K0FG | THM | [27 empty] | THM PP-1-1 = 25/Aug (ETD TNS 4/Aug 5 Aug) | [12 empty] | THM PP-1-2 = 25/Dec (ETD TNS 7/Dec) |  | Base | THM PP-3 = 29 Mar'21 (ETD TNS 25 Mar)
METER ASSY COMB | HP1159-xxx | Pan | [41 empty] | K0FA | THM 1st MP = 6 Apr (ETD TNS 2/Apr)
TNS => THM | [22 empty] | INT 18 JUL'20
37,500/2Y |  | Actual
PP1 23 JUL'20
K0GG | THM | [24 empty] | THM PP-1-1 = 18 Aug (ETD TNS around 29Jul) | [12 empty] | THM PP-1-2 = 15 Dec (ETD TNS around 27 Nov) |  |  |  |  | Base | PP-3 25 Mar ( ETD TNS around 22 Mar)
METER ASSY COMB | 37100-K0GG-A200 | Pan | [41 empty] | K0GA | MP 31 Mar ( ETD TNS around 26 Mar)
TNS => THM | 37100-K0GG-D200 | [25 empty] | INT 15 JUL'20
23,340/2Y | 37100-K0GG-E200 | Actual
| 37100-K0GG-T200 | [25 empty] | PP1 22 JUL'20
HL5L | (NSII) | [9 empty] | 'QC1 - customer : 6-Apr'2020 , NSII : 30-Mar'2020 (ETD TNS 20-Mar'2020 by AIR estimate) | [14 empty] | 'QC2 - customer : 20-July'2020 , NSII : 13-July'2020 (ETD TNS 1-July'2020 by AIR estimate) | [17 empty] | Base
Meter assy | '37200-HL5 -E610-M1 | Pan | [41 empty] | HL5G
TNS => NSII | [22 empty] | INT QC2 17 JUN'20
17,000/2Y |  | Actual
K2LF | THM | [42 empty] | New Full | THM PP-1-1 = Feb (ETD TNS around Mid of Jan)
Meyer Assy Comb | HPXXXXXXXXXXXXX | [43 empty] | THM PP-1-2 = Jun (ETD TNS around Mid of May)
TNS => THM | [44 empty] | PP-2 Aug ( ETD TNS around mid of Jul)
13,000/2Y | [44 empty] | PP-3 Nov ( ETD TNS around Early of Nov)
1st MP Nov ( ETD TNS around Mid of Nov)
K2LA | NSEU | [42 empty] | New Full | 'PP1 sample =HII : Jan'21 & PP1 =HII Feb'21 , NSEU End of Dec'2020(ETD TNS 17-Dec'2020 by AIR)
(NSEU) | [44 empty] | 'PP2 =HII July'21 , NSEU End of Jun'21(ETD TNS 21-Jun'21 by AIR)
TNS--> NSEU-->HII | [44 empty] | 'PP3 =HII Oct'21 , NSEU Early of Sep'21(ETD TNS 18-Aug'21 by AIR)
17,000/2Y | [44 empty] | MP =HII Nov'21 , NSEU Early of Oct'21(ETD TNS 18-Aug'21 by SEA
Cancel this K98G Model
Japan Kubota cannot issue drawings to KCW yet. Because China have problem of Exhaust gas regulations.
I heard situation from Japan Kubota design Dept. below.
お世話になります。クボタ松宮です。
中国の排ガス規制の正規な日程が分かっていないため
現時点でも未定です。
内容は、2019年１２月２３日時点の松宮のメールからの進捗はありません。
出図 不明
初1 2020年未定(KCW組立)
量産 （2021年になりそうだ）未定(KCW組立)
ただし、以前送付いただいた納入承認願い図RF716-53111からの変更計画は現時点でありません。
クボタ 堺製造所 建設機械技術第一部第３チーム松宮 大介（まつみやだいすけ）
Note on B5: 37100-MKP-DA20-M1
Note on B6: 37100-MKP-DL20-M1
Note on B20: 25031-0900
Note on R21: CANCLE
Note on B30: 25031-0901
Note on B45: 25031-0942
Note on B46: 25031-0943
Note on B50: RG156-5311-1
Note on S55: HOLD
Note on B60: HP1151102 K0CX03
Note on B61: HP1151104K0CX01
Note on B62: HP1151103K0CX01
Note on Q64: HOLD PLAN
Note on B65: HP1151154K0CX00
Note on B66: HP1151152K0CX00
Note on B67: HP1151153K0CX00
Note on B70: TC629-3021-1
Note on B100: 37100-K0AJ-TB00
Note on B110: 37100-MKYA-D112-M1, 37100-MKYA-D511-M1,37100-MKYA-C310-M1,37100-MKYA-C511-M1,37100-MKYA-L310-M1, 37100-MKYA-L511-M1
Note on B116: 37100-K1MA-T012-M1
Note on B121: 37100-K2JA-T012-M1
Note on B126: 37100-K2AA-J011-M1
Note on M140: CANCLE
Note on B146: 37100-K2LA-D000
Note on B151: '37100-K2LA-D000

## Summary Jan-Oct '20
[6 empty] | Report by | Saisunee
[6 empty] | Date : | 2019-01-01
New model Summary 2019 - 2020
New Model | Open item all |  | Cose problem | Waiting | Status | MP | Volume
T00A AP2 HATC |  |  |  |  | MP | Jun'20
T00A AP2 HASB |  |  |  |  | MP | Apr'20
T00A 5D |  |  |  |  | DAN May'20 | Dec'20
T00A AP2 HVN |  |  |  |  | DAN Apr'20 | Jul'20
K2EA | 4 |  | 4 |  | MP | Feb'20 | 20,275 pcs/2Y
T20A CBU (RH) |  |  |  |  | DAN0 May'20 | Apr'21
T20A HASB |  |  |  |  | DAN0 Apr'20 | Mar'21
T20A HACBL |  |  |  |  | DAN0 Apr'20
T20A
T20A HCIL |  |  |  |  | DAN0 Dec'20 | Nov'21
Base New model Summary 2019 - 2020 | [6 empty] | Volume
82,144/3Year
New Model | Base Model | Open item all | Cose problem | Waiting | Status | MP | 25/Month
TLAX (CBU) | TLAY | 0 | 0 |  | MP | Apr'20
TLAX (for HPM Desitination) | TLAY | 1 | 1 |  | MP | Apr'20
TLAX (for HTW Desitination) | TLAY | 1 | 1 |  | MP | Jun'20
TLAX (for HCIL Desitination) | TLAY | 1 | 1 |  | MP | Apr'20
TLAX (for HVN Desitination) | TLAY | 1 | 1 |  | MP | Apr'20
TLAX (for HM) | TLAY |  |  |  | MP | Apr'20
4L45W 20MY | 4P45 |  |  |  | MP | Jun'20
4B45V 20MY |  |  |  |  | PT Jul'20 | WAITING
MKYA | MKNA | - | - |  | PP1 Feb'20 | Aug'20 | 43,100 pcs/2Y
MKPF | MKPA | 0 | 0 |  | PP3 Jun'20 | Jul'20 | 35,119 pcs/2Y
C69 | C53 EU | 0 | 0 |  | MP | Feb'20 | 1,800/Y
3905 21MY | 3905 | 0 | 0 |  | Pilot May'19 | Aug'20 | 13,000 pcs/2Y
2504 | 8896 | 5 | 5 |  | MP | Feb'20 | 18,555/2Y
4810 21MY | 4810 Current | 0 | 0 |  | Pilot Jun'20 | Nov'20 | 21,600/2Y
SCM7T4 | MB43 | 0 | 0 |  | Pilot1 July'20 | Oct'20 | 1,000/Y
8121 / 8122 | 8020/8022 | - | - |  | Pilot May'20 | Sep'20 | 9,615/2Y
K1BA (STD TYPE) | K0BA | - | - |  | PP2 Apr'20 | Jun'20 | 32,400/2Y
K1BA (SEB TYPE) | K0BA | - | - |  | PP2 Apr'21 | Jun'21 | 8,820/2Y
K1BF | K0BF | - | - |  | PP2 Jun'20 | Oct'20 | 22,000/2Y
K40H | K40G | - | - |  | PP2 Jun'20 | Sep'20 | 22,000/2Y
K1TA | KZZJ | - | - |  | PP1 Apr'20 | Sep'20 | 32,700 pcs/2Y
K98G | K98A | - | - |  | PP1 Jun'20 | Oct'20 | 15,420 pcs/2Y
K26P | K26J | - | - |  | PP1 Apr'20 | Sep'20 | 89,080 pcs/2Y
K0AJ | K0AH | - | - |  | PP1 Apr'20 | Oct'20 | 18,967 pcs/2Y
K1MA-TA | K76L | - | - |  | PP1 Mar'20 | Aug'20 | 137,400/2Y
K1MA-W000 => K2JA | K58M | - | - |  | PP1 Jun'20 | Dec'20 | 1,258,200/2Y
E67 | E62 | - | - |  | Pilot1 Jun'20 | Sep'20 | 840/Y
MB23SI | MB43 | - | - |  | Pilot2 Mar'20 | Nov'20 | 50 pcs/Y
K2AA | K1BA | - | - |  | PP1 Jan'20 | Jun'20 | 8,600/2Y
K0FG | K0FA | - | - |  | PP1-1 Jun'20 | Mar'21 | 37,500/2Y
Note on B45: Waiting THM update schedule